## Sheet1
backlog
id | type | desc | owner | status | priority
TTN-1 | story | create html page | yoni | done | 1
TTN-2 | story | create commants list | moshe | done | 2
TTN-3 | story | add copy to clipboard | yoni | waiting | 1
TTN-4 | story | add styles | moshe | done | 1
TTN-5 | story | add links as referecnes | moshe | inProgress | 3
TTN-6 | story | add login/ signup |  |  | 2
TTN-7 | bug | change header to be bigger |  |  | 2
TTN-8 | bug |  |  |  | 3
TTN-9
TTN-10
TTN-11
TTN-12
TTN-13
TTN-14
TTN-15
TTN-16
| bug | counter should start when clicking on the first correct number (the cell with the number one) |  |  | 1